Terms of Reference for the Consultancy work

For facilitating disaster/emergency management planning training at district level

Introduction

In April 2012, Oxfam and the Directorate General for Humanitarian Aid and Civil Protection signed an agreement (ECHO/DIP/BUD/2012/91004) on the implementation of the DIPECHO 7 project on Promoting community based Disaster Prevention and Disaster Risk Reduction practices in Tajikistan.

Context of this consultancy

Part of the project focuses on capacity building of the local partners, community and local authorities in emergency planning both at task –specific and more strategic and long range levels.  It is envisaged that 2 districts of Khatlon district will benefit from the capacity building exercise in developing emergency management plans at local levels that will ensure effective and efficient response to natural disasters in their locality.

Scope of work

The candidate will work as Disaster Management Planning Consultant by supporting the development of an evidence-based disaster planning training in 2 pilot districts of East Khatlon, where Oxfam is implementing DIPECHO 7 project.

A team player with a proven track record of initiative, the Consultant  will capture the  context specific requirements and needs, facilitate capacity building of local stakeholders and  document planning process and share lessons learned with partners and stakeholders so that best practices can be identified, understood and replicated in other regions on multi- stakeholder disaster management planning at district level .

Specific duties are as follows:

- Capacity-building on disaster / emergency management planning: Develop and implement orientation modules on key disaster management planning strategies and tools to ensure effective coordination and buy-in of partners and stakeholders.

The goal of this capacity building exercise will be to enable the identified districts authorities to:

- define the potential natural disasters and emergencies that could affect their jurisdictional area

- conduct an assessment of the risk of occurrence and the potential impact of a hazard on people and property within their jurisdictional area

- establish procedures for review and revision of local emergency plans

- conduct training and exercises for all emergency response staff

- identify procedures for obtaining emergency resources, including personnel, equipment, facilities and financial resources

- establish procedures by which the local emergency plan is to be implemented

- establish procedures for notifying persons threatened by emergencies

- coordinate the provision of food, clothing, shelter, transportation, and medical services to victims of emergencies

- establish priorities for restoring essential services

- Learning and knowledge sharing: Capture, document and share learning from disaster management planning at district level based on the facilitation of the events/workshops in 2 districts.

- Capture and share progress of stakeholders in workshops, meetings and other channels on disaster management planning at district level.

- Provide an analysis for future advocacy work in the field of disaster management planning at district level.

The consultant will be responsible to deliver on 4 main areas captured below based on the aforementioned scope of work under section A and B:

- With support from OXFAM DRR team , consultant will  organize the capacity building and planning activities in 2 pilot districts on the aforementioned 9 areas under section A ;

- facilitation natural hazard  risk and assessment and vulnerability in each district with local authorities

- facilitate compilation and completion of the district natural  disaster management planning document

- Produce lessons learned document with analysis of the context for the future advocacy work

Timing and Level of Effort:  3 weeks in November of 2012. This consultancy is for 15 working days.

The activities will include:

Desk review, module development, training, HRVA exercise and report write up.

Qualifications/Job Requirements

Must be able to commit for a minimum 15-day assignment and be able to travel to Dushanbe and Kulyab, Tajikistan.

1. Bachelor (masters preferred) in Emergency Management, Engineering, Planning, Geography, or related field from a reputable university.

2. Minimum of 8 years of relevant experience disaster / emergency management planning.

3. Knowledge of and experience in interpreting and using qualitative and/or quantitative research to develop evidence-based strategies.

4. Strong conceptual and analytical skills.

5. Experience in training and capacity building.

6. Track record of initiative and proven ability to work independently with minimal supervision.

7. Strong interpersonal skills and ability to work in a multi-disciplinary team.

8. Excellent verbal and written communication and presentational skills.

9. Strong communication skills in English, Russian or Tajik desirable.

10. Ability and willingness to travel to the field.

11. Computer proficiency (Office software, internet and email).

Management and Reporting

The consultant will report to and DIPECHO programme Manager/ Deputy Country Director.