IDRC, Workshop on National Platforms, 23-29 August 2009

Action Plan – Tajikistan

DRR coordination mechanism

Authors: Mr. Alisho Shomahmadov, Committee of Emergency Situations and Civil Defence under the Government of Tajikistan, Mr. Sulton Rahimov, International Fund for Saving the Aral Sea, Ms. Gulsara Pulatova, UN ISDR Central Asia, Ms. Zulfia Mirbaeva, Geophysical Survey Tajikistan, Mr. Malik Ajani, FOCUS Humanitarian Assistance Tajikistan, Mr. Khusrav Sharifov, UNDP Tajikistan

Moderator: Mr. Matthias Anderegg, SDC Tajikistan

Version/Date: 1/ 27 August 2008

Problem Tree:

| - State Commission on Emergency Situations is not functional; | - Weak coordination; |
| --- | --- |
| - Law capacity (Commission and CoES); | - Too much UN Coordination (but no other alternative); |
| - Lack of funds (law salaries); | - Climate change issues; |
| - Lack of involvement from private sector; | - Migration; |
| - Law priority given by Govt to DRR; | - Poor monitoring of hazardous processes; |
| - Changes in the Govt; | - Response oriented system; |
| - Uncertainties; | - Education/training (specialists – schools, universities); |
| - Lack of political will; | - Brain drain; |
| - Corruption |  |

Action Plan

Overall Goal: People of Tajikistan are disaster resilient

Objective: Strengthened existing national coordination mechanisms

| # | Action line | How it is done? | Who leads the process? | Who pays for it |
| --- | --- | --- | --- | --- |
| 1 | Advocating involvement of high level decision makers and partners | - meeting with UN RC; - meeting with Deputy Prime (Mr. Ghulomov); - discussions through REACT | CoES (supported by UNDP, UN ISDR, REACT) | Govt, ECHO-UNDP Project supporting REACT |
| 2 | Strengthening the secretariat of State Commission on ES | - details to be discussed in TJK; | Deputy Prime Minister (supported by CoES, UNDP, UN ISDR) | Govt, other donors (SDC, ECHO, etc) |
| 3 | Suggestions of changes to ToR of State Commission | - through discussions at REACT; - support from UN RC, donors; - agreement with Deputy Prime Minister (Mr. Ghulomov) | Deputy Prime Minister (supported by commission secretariat, CoES, UNDP, UN ISDR) | Govt |
| 4 | Approve National Disaster Risk Management Strategy by Govt of Tajikistan | - a process agreed with CoES and wider Govt working group; - REACT | CoES (supported by UNDP, UN ISDR, REACT partners) | Govt, ECHO – UNDP project |
| 5 | Approve National Disaster Preparedness and Response Plan by Govt of Tajikistan | - a process agreed with CoES and wider Govt working group; - REACT | CoES (supported by UNDP, UN ISDR, REACT partners) | Govt, ECHO – UNDP project |
| 6 | Integrate DRR into strategies and programmes (NDS, PRSP, JCSS, UNDAF, etc) | - involvement in processes of developing and revising these strategic documents; | Govt (supported by UN, IFIs, donors and REACT partners) | Govt, other donors (SDC, ECHO, WB, ADB) |
| 7 | Implement DRR strategies and plans |  | Govt (supported by UN, IFIs, donors, REACT partners) | Govt, other donors (SDC, ECHO, WB, ADB) |