CONTEXT

- Nicaragua has, since 2000, an adequate legal framework (law 337) that offers guidelines  and regulations for the creation and institutionalization of a DRR System which has actually existed already for the last 8 years.

- The functioning of the system includes  responsibilities on prevention, mitigation, preparedness, attention and recovery, involving key government institutions, as well as sectoral commissions that include sectoral focal points

- A national curricula on RRD for the educational system has been designed   and  it is being gradually implemented

- Many of the existing 153 municipalities already have hazard and risk maps, response plans and committees on RRD.

- A few strong NGO support the system and are developing RRD capacities on prevention and attention

- Within the 337 law framework an executive secretariat was created as the system’s main coordinating mechanism, but so far it  has had limited coordinating and articulating capacities which need strengthening

IDRC, Workshop on National Platforms, 23-29 August 2009

Action Plan Nicaragua X

Authors:INETER, DEFENSA CIVIL-IPADE

| HFA AP | Action line Objective with short description | How is it done? Activity | Who does it? Institution/responsible person | Who pays for it? internal – request to | Remarks Context/Risks |
| --- | --- | --- | --- | --- | --- |
| 1 | Making Disaster Risk Reduction a Priority |  |  |  |  |
| 1.1 | Multistakeholder Dialogue |  |  |  |  |
| 1.2 | Coordination Mechanisms |  |  |  |  |
|  | Strengthening the HFA accomplishment improving the coordination and internal communication in SINAPRED functioning | Creation of a system catalyzing group with the key actors of greater strength | Executive Secretary, Civil Defense, INETER, MINSA, MTI | Institutional |  |
|  |  | Integration of short and medium term planning as an axis to improve the system articulation | Executive Secretary | Institutional |  |
|  |  | National Plan for Risk Management Updating, including climate change adaptation | Executive Secretary | Institutional |  |
|  |  | Other actors integration (NGOs, Private Sector) | SINAPRED:INETER, CIVIL DEFENCE, NGOs/IPADE | Institutional |  |
| 1.3 | Institutional Basis |  |  |  |  |
| 1.4 | Prioritization and Resources |  |  |  |  |
|  | Development of a more understanding and awareness on risk management and climatic change adaptation | Inventory of existing educational and dissemination materials | SINAPRED:Civil Defence, INETER, NGOs/IPADE | Institutional and International Cooperation |  |
|  |  | Quality standards definition for those materials and make them official through SINAPRED | Idem | Idem |  |
|  |  | Diffusion of those materials according to priorities (National, local or specialized) | SINAPRED, MED, Civil Defense | Idem |  |
|  |  | Support the Ministry of Education in the promotion of a preventive culture by means of integrating risk management into the curricula of the general basic education | SINAPRED, NGO, | Institutional and International Cooperation, COSUDE |  |
|  |  | Awareness raising, training and education of mass media as educational agents on risk management | SINAPRED, CIVIL DEFENCE, ONG, | Institutional and International Cooperation, COSUDE |  |
|  |  | Continuing the local risk management committees preparation | SINAPRED: Civil Defence, ONG, local govts. |  |  |
|  |  | Strengthen the research on climate change and risk management | SINAPRED: INETER, MARENA, Universities, ONG | Institutional and International Cooperation |  |
|  |  | Promoting the integration of the climate change approach into the risk management | SINAPRED: INETER, MARENA, CIVIL DEFENCE, NGOs/NGO | Institucional |  |
|  | Risk reduction capacity building among key institutions of SINAPRED | Improving the Civil Defence capacities and equipment for the preparation of the population on risk management | SINAPRED: Civil Defense | Institutional and International Cooperation |  |
|  |  | Strengthening the technical and scientific capacities of INETER – for observation, processing and analysis. | SINAPRED: INETER, | Institutional and International Cooperation |  |

Version/Date: 29.08.08