IDRC, Workshop on National Platforms, 23-29 August 2009

Action Plan  Mozambique

Authors: Dulce Chilundo, Augusto Fermino, Susanne Neymeyer

Facilitator: Karl-Otto Zentel

| HFA AP | Action line Objective with short description | How is it done? Activity | Who does it? Institution/responsible person | Who pays for it? internal – request to | Remarks Context/Risks |
| --- | --- | --- | --- | --- | --- |
| 1 | Making Disaster Risk Reduction a Priority |  |  |  |  |
| 1.1 | Multistakeholder Dialogue |  |  |  |  |
|  | Strengthen the coordination | Regular meeting with the main stakeholders Evaluation and sharing results and lessons learned | CENOE Joint evaluation | No extra cost Shared cost of every stakeholder | ------ INGC/CENOE take the lead |
|  | Stream down to provinces | On provincial level | COE (leaded by Provincial Permanent Secretay) | No extra cost | ----- |
|  | Strengthen the infrastructure cluster group | High level dialog among stakeholders | Government/stakeholders – UN Habitat, and others | No cost | If resources are mobilized to assist affected people would quickly resettle and avoid moving back to risk areas |
| 1.2 | Coordination Mechanisms |  |  |  |  |
|  | Set up coordination in provincial level | Provincial government has to take the lead Make a regular meetings | Provincial Permanent Secretary | Each stakeholder | Command from the Primer Minster and Advisor from the General Director of INGC |
| 1.3 | Institutional Basis |  |  |  |  |
|  | INGC | See above | INGC and its stakeholders | INGG/Government | Needs some improvement in leadership and according to analyzed gaps in Master Plan. Training in evaluation |
| 1.4 | Prioritization and Resources |  |  |  |  |
|  | Evaluation and sharing results and lessons learned |  |  | Training capacity Funding |  |
|  | Strengthen the infrastructure cluster group |  |  | Staff and commitment |  |
|  | High level dialog among stakeholders |  |  | High level commitment |  |
|  | Set up coordination in provincial level |  |  | Command from Prime minister | Advisor from the INGC to Primer Minister Cabinet |

Version/Date: 27/08/08